## Cost tracker
Construction cost tracker
Free template from I-Cost (i-cost.co.uk). Type in the yellow cells; everything else is worked out for you.
Project | Example project
Agreed contract value (£) | 250000
Code | Area / package | Cost type | Budget (£) | Ordered (£) | Invoiced (£) | Committed (£) | Remaining budget (£) | Forecast final cost (£) | Variance (£) | % of budget committed | Notes
1.1 | Groundworks | Subcontract | 42000 | 40500 | 18000
1.2 | Concrete frame | Materials | 38000 | 41200 | 41200
2.1 | Drylining and ceilings | Subcontract | 31000 | 29800 | 0
2.2 | Site labour | Labour | 22000 | 9500 | 9500
3.1 | Mechanical and electrical | Subcontract | 54000 | 0 | 0
4.1 | Preliminaries | Preliminaries | 18000 | 6000 | 6000
Totals
Summary
Contract value
Budget (cost)
Committed so far
Forecast final cost
Cost to complete (forecast - committed)
Forecast margin (£)
Forecast margin (%)
How the forecast works: each line is forecast at its budget, or at what is committed if that is more. Committed is the order value or the invoices, whichever is higher.
Outgrowing this sheet? I-Cost keeps budget, orders, invoices, deliveries and site hours up to date automatically: https://i-cost.co.uk/construction-cost-tracking/

## How to use
How to use this cost tracker
1. Type the project name and the agreed contract value at the top.
2. Add one line per area, package or cost code, with its budget (the estimate at cost).
3. When you place an order, add its value to Ordered. When an invoice arrives, add it to Invoiced.
4. Committed, Remaining, Forecast and Variance are worked out for you. Red figures mean over budget.
5. Check the Summary every week: forecast final cost and forecast margin.
Tips
- Record orders when you place them, not when the invoice arrives: that is when the money is committed.
- Add site labour weekly from timesheets so labour cost is never a surprise.
- Keep one line per package so you can see exactly where the margin is moving.
Made by I-Cost, construction estimating and cost control software for UK contractors: https://i-cost.co.uk/